## Cyclogram
Actuator | Movement | Waits for (an actuator above) | Until it has | Offset s | Stroke out s | At the end position s | Stroke back s | Start s | Arrived s | Released s | End s | Total s | Cycle time s | Sequential sum s
Move to position | Slide out and back |  |  | 0 | 0.5 | 1.5 | 0.5
Clamp | Clamp the bush | Move to position | arrived | 0 | 0.4 | 0.8 | 0.4
Drill | Drill the hole | Clamp | arrived | 0 | 0.3 | 0.5 | 0.3
Eject | Air jet | Move to position | finished | 0 | 0.2 | 0.1 | 0.2
How to use: one row per movement. Name the actuator, type the three parts in seconds, and in “Waits for” name the actuator whose movement this one cannot start before — “arrived” waits for the end of its stroke out, “finished” for the end of its stroke back. Leave “Waits for” empty for a movement that starts the cycle. The offset is deliberate dead time (valve response, a settle). Start, Arrived, Released, End and the cycle time are computed; the Chart sheet draws the bars.
Limits: one predecessor per movement (for two, take the later one by hand), one movement per actuator, no wrap across the cycle end, and no check that two movements overlap in a place they must not — look down the chart for that. cyclogram.app/learn/cyclogram-template/ explains; cyclogram.app/app/ does all of it live.

## Chart
Movement | 0 | 0.1 | 0.2 | 0.3 | 0.4 | 0.5 | 0.6 | 0.7 | 0.8 | 0.9 | 1 | 1.1 | 1.2 | 1.3 | 1.4 | 1.5 | 1.6 | 1.7 | 1.8 | 1.9 | 2 | 2.1 | 2.2 | 2.3 | 2.4 | 2.5 | 2.6 | 2.7 | 2.8 | 2.9 | 3 | 3.1 | 3.2 | 3.3 | 3.4 | 3.5 | 3.6 | 3.7 | 3.8 | 3.9 | 4 | 4.1 | 4.2 | 4.3 | 4.4 | 4.5 | 4.6 | 4.7 | 4.8 | 4.9 | 5 | 5.1 | 5.2 | 5.3 | 5.4 | 5.5 | 5.6 | 5.7 | 5.8 | 5.9 | 6
Each cell is 0.1 s. ░ stroke out or back, █ at the end position. Read down a column to see what the whole machine is doing at that instant; the cycle time on the Cyclogram sheet is where the last bar ends.